## Progress as on date
PROJECT: GAME ON SELF DRIVING CAR |  | GANTT CHART |  |  |  |  | Legends |  | Completed
In progress
|  | W-1 | W-2 | W-3 | W-4 | W-5 | W-6 | W-7 | W-8
Sr. No. | Description | 2020-01-15 | 2020-01-22 | 2020-01-29 | 2020-02-05 | 2020-02-12 | 2020-02-19 | 2020-02-26 | 2020-03-04
A | TEAM MEETINGS
1 | Got together in the group and discussed few topics about the project and decided to do a project - "WATCH IT QUICKLY" that is one can extract useful information from the videos and share it to our friends. | bar: 2020-01-15
B | REQUIREMENTS AND SPECIFICATIONS OF THE PROJECT
1 | On further discussion, we finalsed to work on the artificial intelligence algorithm and decided to create a game on self driving car simulation by learning from Udemy course. After taking from the professor, we have submitted the abstract for the same. | bar: 2020-01-22
C | LEARNING PHASE
1 | Started working actively by clearing the fundamentals on AI by studying some papers and watching several video. And we prepared a learning document on "LEARN HOW TO BUILD AN AI" | bar: 2020-01-29
D | DESIGN PHASE
1 | Created the structure of the project. We divided the project into different branches like: car_interface, car_graphics , car_ai_algo and development. | bar: 2020-02-05
E | IMPLEMENTATION
Worked on the car_graphics.kv file and updated the same.
1 | Prepared the car model with detailed description on the car features-dimensions,orientation, sensors shape and colour. | bar: 2020-02-12
Updated the sensor shape
2 | Added some changes to the previous file to improve the functionality | bar: 2020-02-19
Coding
3 | Interface for graphics created and committed as map.py file | bar: 2020-02-26 to 2020-03-04
Coding
4 | Learning the algorithms of deep learning and started working on "ai.py" file | bar: 2020-02-26 to 2020-03-04
D | UNIT TESTING
1 | Tested the car model by integrating the kivy file with the python file and made changes in the code accordingly | bar: 2020-02-26 to 2020-03-04